## Instructions
Harness Feedback → Feature Suggestion Tracker
BA improvement loop: collect QA feedback on Harness → cluster & prioritize → propose feature/UX changes
Scope | QA authors and runs test cases in Harness. We do NOT. Our job is to improve Harness: gather QA's feedback, group it into root causes, and propose concrete feature/UX changes for the dev team to build.
Tab 1 — Feedback Log | Raw intake, one row per piece of QA feedback. Low friction: QA (or you) drops the complaint here; we do the structuring. Pre-seeded with the 11 items from QG-139.
Tab 2 — Suggestions | Our output: proposed features/changes, each with a placement + default behavior and an Impact×Effort priority. Links back to the Feedback IDs it resolves. Pre-seeded with recommendations for QG-139.
Tab 3 — Dashboard | Live counts by category, priority, and status. Pulls from the other two tabs automatically.
Categories | Functional bug · Missing feature · Traceability gap · UX friction · Performance. Tag every feedback item so patterns emerge.
Priority | Impact × Effort. Do first (high impact / low effort) · Do next (high impact / high effort) · Plan carefully (needs design) · Nice to have. Confirm effort with dev before committing.
Cluster, don't list | Several complaints often share one root cause (e.g. 'can't find my stuff' = no tagging/filtering). Group symptoms into causes so dev fixes causes, not symptoms.
Since Harness is internal | Suggestions convert directly into Jira dev stories — not third-party feature requests.

## Feedback Log
Feedback Log — raw QA input on Harness
FB ID | Date | Source | Harness Area | Category | Feedback (raw) | Impact | Frequency | Linked Jira | Status
FB-001 | 2026-07-03 | QA (QG-139) | Prompt list | Missing feature | Enable search within prompt contents. | Medium |  | QG-139 | New
FB-002 | 2026-07-03 | QA (QG-139) | Test Cases | Missing feature | Test cases can't be tagged or filtered by feature (e.g. Rating, Cash Forecast). Want Jira-style tags. | High |  | QG-139 | New
FB-003 | 2026-07-03 | QA (QG-139) | Tasks / Runs | Missing feature | No filter to view only my own tasks; tasks aren't in chronological order, hard to track a person's work. | High |  | QG-139 | New
FB-004 | 2026-07-03 | QA (QG-139) | Global UI | UX friction | Page refresh rate too fast — visually jarring and uncomfortable. | High |  | QG-139 | New
FB-005 | 2026-07-03 | QA (QG-139) | Activity Log | Missing feature | Need a download button to export activity log to .txt or .md. | Medium |  | QG-139 | New
FB-006 | 2026-07-03 | QA (QG-139) | Test Case Details | Traceability gap | Only see Pass/Fail, not actual output data — can't manually verify accuracy. | High |  | QG-139 | New
FB-007 | 2026-07-03 | QA (QG-139) | Runs / Results | Traceability gap | Hard to tell which Request a test-case result belongs to (one request = many results). | High |  | QG-139 | New
FB-008 | 2026-07-03 | QA (QG-139) | Stopping condition | UX friction | Correct and optimize the UX workflow for the stopping-condition feature. | Medium |  | QG-139 | New
FB-009 | 2026-07-03 | QA (QG-139) | Test Cases | Missing feature | Need a process to validate and handle duplicate test cases. | Medium |  | QG-139 | New
FB-010 | 2026-07-03 | QA | Runs tab | Traceability gap | Let users click any row in Runs to go straight to Test Case Details. | Medium |  | QG-139 | New
FB-011 | 2026-07-03 | QA | Prompt input | Missing feature | Support line breaks in prompt input; on failure, point out the exact line that failed. | Medium |  | QG-139 | New
FB-012 | 2026-07-06 | QA / BA | Requests queue | Traceability gap | Can't tell which requests are mine — no creator/owner or title shown in the queue; must open each one. 'Created by' exists only on Info tab. | High | 3 (Teams) | QG-139 | Reviewing
FB-013 | 2026-07-06 | BA / QA | Requests | UX friction | Request IDs are raw UUIDs; must memorize them to trace your own work. Hard to reference in Teams/Jira. | High | 2 (Teams) |  | Reviewing
FB-014 | 2026-07-06 | BA observation | Requests queue | Missing feature | No search or filter in the Requests queue (by creator, status, content, or date). | High |  |  | Reviewing
FB-015 | 2026-07-06 | BA observation | Dashboard / Runs | Functional bug | AI steps = 0 on every run (KPI, AI-step-ratio 0%, step-mix has no AI bars). LLM path appears unused or not captured. | High |  |  | New
FB-016 | 2026-07-06 | BA observation | Executed history | Functional bug | Failure screenshot shows an unrelated site (OOYOD Cash Flow), not Aloha — possible navigation/session drift. | High |  |  | New
FB-017 | 2026-07-06 | BA observation | All cases | Functional bug | Right-hand detail panel is duplicated/stacked when selecting one case (rendering bug). | Medium |  |  | New
FB-018 | 2026-07-06 | BA observation | All / Dashboard | Missing feature | Category always 'default' and cases 'unlabeled' — taxonomy unused, so dashboard breakdown and filters are inert. | Medium |  | QG-139 | New
FB-019 | 2026-07-06 | BA observation | Failed | Traceability gap | Failure screenshot placeholder is empty; error output shows a file path (error-context.md) not the content inline. | Medium |  | QG-139 | New
FB-020 | 2026-07-06 | BA observation | Failed | UX friction | 9 of 10 failures stuck in 'Needs triage' — reason assignment too slow / not prompted. | Medium |  |  | New
FB-021
FB-022
FB-023
FB-024
FB-025
FB-026
FB-027
FB-028
FB-029
FB-030
FB-031
FB-032
FB-033
FB-034
FB-035

## Suggestions
Suggestions — our proposed Harness improvements (dev-ready)
FS ID | Resolves (FB IDs) | Proposed change | Placement / default behavior | Impact | Effort | Priority | Status
FS-001 | FB-006 | Show actual output on Test Case Details | Add an 'Actual Output' section beside Expected so QA can verify a Pass is truly correct. | High | Med | Do first | Proposed
FS-002 | FB-010 | Clickable Runs rows | Make the whole Runs row open Test Case Details, with a hover state. | Med | Low | Do first | Proposed
FS-003 | FB-004 | Fix refresh behavior | Replace timed full-page refresh with a manual Refresh button + 'updated 30s ago', or row-level live updates. | High | Med | Do first | Proposed
FS-004 | FB-005 | Activity-log export | Download button top-right of the log panel; export .txt/.md with a date-range picker. | Med | Low | Do first | Proposed
FS-005 | FB-002 | Test-case tagging & filtering | Jira-style tag field on create/edit (free-create + select); filter chips atop Runs and Test Case lists. | High | High | Do next | Proposed
FS-006 | FB-003 | Assignee filter + chronological sort | 'Assignee' dropdown with one-click 'My tasks' toggle; secondary sort by created-date. | High | Med | Do next | Proposed
FS-007 | FB-007 | Case → request mapping | Persistent Request ID/name breadcrumb on every result row + details page; group results under their request. | High | Med | Do next | Proposed
FS-008 | FB-008 | Stopping-condition workflow | Move config into run-setup with plain-language options; clear indicator when it fired and why. Needs discovery screenshots. | Med | High | Plan carefully | Proposed
FS-009 | FB-009 | Duplicate validation | On submit, warn 'Possible duplicate of #123 — create/merge?'; background dedupe report. Define matching rule with team. | Med | High | Plan carefully | Proposed
FS-010 | FB-011 | Line-level prompt error tracking | Support line breaks in prompt input; on failure cite the exact failing line. | Med | High | Plan carefully | Proposed
FS-011 | FB-001 | Prompt content search | Search box top-left of prompt list, placeholder 'Search prompt contents…'; search body text, debounced. | Med | Med | Nice to have | Proposed
FS-012 | FB-012 FB-013 | Enrich Requests queue rows | Each row shows title preview + Created by + created time + status + case count + friendly REQ-#### ref. Resolves 'which request is mine'. | High | Low | Do first | Proposed
FS-013 | FB-012 FB-014 | Requests filter + search toolbar | Above the queue: 'My requests' one-click toggle (primary) + Created-by + Status + content/ID search + date range. Newest-first default. | High | Med | Do first | Proposed
FS-014 | FB-013 | Human-friendly request reference | Sequential REQ-#### shown to users + Copy button; keep UUID internal. Paste into Teams/Jira instead of a 36-char UUID. | Med | Low | Do next | Proposed
FS-015 | FB-015 | Clarify/fix AI-step usage | Investigate why AI steps = 0; either fix telemetry/agent path or hide AI charts until wired. Needs PO/dev answer. | High | High | Plan carefully | Proposed
FS-016 | FB-016 FB-019 | Reliable failure evidence | Ensure failure screenshots are captured & rendered; surface error-context.md content inline (expandable). Investigate wrong-site capture. | High | Med | Do next | Proposed
FS-017 | FB-017 | Fix All-cases panel duplication | Detail panel should replace, not append, on selection. Rendering bug fix. | Med | Low | Do first | Proposed
FS-018 | FB-018 | Stand up real taxonomy | Replace 'default'/'unlabeled' with usable categories/tags; make dashboard rows click-through. Unlocks filtering + reporting. Overlaps FS-005. | High | High | Do next | Proposed
FS-019
FS-020
FS-021
FS-022
FS-023

## Dashboard
Dashboard
Live counts from Feedback Log and Suggestions.
Feedback by Category |  | Suggestions by Priority
Category | Count | Priority | Count
Functional bug | 3 | Do first | 7
Missing feature | 8 | Do next | 6
Traceability gap | 5 | Plan carefully | 4
UX friction | 4 | Nice to have | 1
Performance | 0
Feedback by Status
Status | Count
New | 17
Reviewing | 3
Proposed | 0
Accepted | 0
Done | 0
Rejected | 0